## Introduction
Object Oriented Programming Project Management Sheet
Use this sheet to manage your project. It consists of the following tabs:
(1) | TaskList | The recorder maintains this worksheet To Start: Make your list of user stories Assign a priorit to each story from the dropdown list Estimate the time required for each story Set the status of each story to 1 as ToDO Set the % Done of each story to 0 as it has not been started yet At the start of each sprint: Choose which stories to focus on for the current sprint Set dues dates for each story Assign owners to each story Change the status of chosen stories to -1 for in progress At each session during a sprint: Check the progress of each story and change the % done accordingly Change the status of complete stories Log any comments, issues or new stories that have emerged
(2) | Burndown | The SCRUM master maintains this tab during the sprint. At the end of each session the amount of work in hours left to be completed is taken from the tasklist and rekeyed into this tab. By recording the work left to do the burn down chart for the team can be viewed which shows the estimated amount of work that needs to be completed before the project delivery date. The main activities and deliverables of each meeting should be recorded here. Looking at the graph it is obvious when additional resources are needed, or the current resources need to do more hours or the scope of the work is too big for the timeline - so a feature may need to be dropped.
(3) | Control | The control sheet contains the values that are used in the cell drop down Before starting the project replace the Resources section entries with the names of your team
(4) | Example | This tab shows an example of a filled in burn down chart where each day the hours left to be completed was noted.
This value here is the one to rekey into the burndown sheet
Put your names here
Goto Tasklist
Goto Burndown
Goto Control
Goto Example
Goto Resources

## TasksList
| TASKS LIST |  |  | Status : 1 = todo, -1 = doing, 0 = complete, d = deleted |  |  | Each day transfer burndown value to burn down sheet
|  |  |  | Estimated |  |  | Enter date | 23
Ref | Type | Stories | Priority | Hours to do | Status | % Done | Due By | BurnCalc | Sprint | Owner | Comment | Issues encountered | If Demoted explain why
US-0001 | Requirements & Design | Talk with secondary school students to discover what part or maths and science they find most difficult and how they think an mobile phone app might help OR ask tell them your idea and see what they think | 1 | 12 | 0 | 100% | 2012-02-07 | 0 | Sprint 0 - concept & plan | Adam Wade | Questions. Do you you find that visual aids such as charts and diagrams assist with your learning? Would you like a leaderboard system to be implimented into the appilication? How would you like to see the application on the screen? | No issues encountered
US-0002 | Planning | Do a rought sketch of the application. Each member fo the group is going to brainstorm and come up with different ideas on the GUI and how we should take the issue forward | 1 | 48 | 0 | 100% | Thurs 09 Feb | 0 |  | Adam Wade | We drew a rough sketch in fireworks of the mock up for our project. | No issues encountered
US-0003 | Planning | Learn about NetBeans and try to get used to the basics of the appilcation | 1 | 1596 | 0 | 100% | Week 11 | 0 |  | Adam Wade | Learned about it in class. But will still continue to learn more as time goes on. | No issues encountered
US-0004 | Research | Research similar types of games for ideas we can use for our own. | 1 | 12 | 0 | 100% | Thurs 16 Feb | 0 |  | Adam Wade | Research different types of game for ideas. Decided on a maths game
US-0005 | Planning | Figure out which types of maths we're going to be focusing on for the project | 1 | 2 | d | 100% | Thurs 09 Feb | 0 |  | Adam Wade | Decided to base our projecton technology insteadof maths. | No issues encountered
US-0006 | Planning | Find visual aids and Gifs to help make the game more interesting for the player | 1 |  | 0 | 100% |  | 0 |  | Adam Wade | Found visual aids such as pictures on gifs that we will use for our games on the internet | No issues encountered
US-0007 | Planning | Do mockup of project. | 1 | 2 | 0 | 100% | Thurs 09 Feb | 0 |  | Adam Wade | Done in fireworks and uploaded | No issues encountered
US-0008 | Testing | Put the GUI in netbeans | 1 | 2 | 0 | 100% | Thurs 16 Feb | 0 |  | Adam Wade | Arnis designed the netbeans mock up and uploaded it | No issues encountered
US-0009 | Requirements & Design | Barry is doing the design for the logic page | 1 | 12 | 0 | 100% | tues 21 Feb | 0 |  | Adam Wade | Barry uploaded the logic design to moodle. | No issues encountered
US-0010 | Requirements & Design | Brian and Adam are doing the design for the probobility page | 1 | 12 | d | 0% | Thurs 23 Feb | 0 |  | Paul Cuffe | Idea Terminated. |  | It's not on the Curriculum, and we've decided to do our app on truth tables.
US-0012 | Requirements & Design | Design a leaderboad to mark scores and points. | 1 | 12 | 0 | 100% | Thurs 23 Feb | 0 |  | Paul Cuffe | Still in progress.
US-0013 | Art / Sound Assets | Research ideas for what type of games we will have for the implication section. | 2 | 1 Week | 0 | 100% | Tues 28 Feb | 0 |  | Paul Cuffe | Complete
US-0014 | Programming | Arnis will make sure the program runs well in NetBeans. | 1 | 12 | 0 | 100% | Thurs 23 Feb | 0 |  | Paul Cuffe | User can nonw switch between pages in our app.
US-0015 | Requirements & Design | Barry will try and get the Truth tables working. | 2 | 20 | 0 | 100% | Tues 28 Feb | 0 |  | Paul Cuffe | truth tables page is now completed.
US-0016 | Requirements & Design | The design that was made in flash is going to be incorporated with the Truth tables. | 1 | 20 | d | 0% | Thurs 1 Mar | 0 |  | Paul Cuffe | Decided to create game in netbeans rather then in Flas.
US-0017 | Requirements & Design | The designing of Logic Circuit Pages. | 1 | 2 | 0 | 100% | Thurs 1 Mar | 0 |  | Paul Cuffe | Design completed in NetBeans
US-0018 | Planning | We are looking into Logic Circuits game to see if they can be applied to our project. | 1 | 1 Week | 0 | 100% | Thurs 8 Mar | 0 |  | Paul Cuffe | We have deicded to try and make the game in Flash first and it will be in the form of a jigsaw-type game
US-0019 | Planning | Positions were changed for sprint 2. Adam Wade has been promoted to scrum master. Brian Wong has now taken the position of notetaker. | 0 | 0 | 0 | 100% | Tues 6th Mar | 0 |  | Brian Wong | Complete
US-0020 | Research | Looked up codes that would be suitable to implement into our application. | 1 | 5 | 0 | 100% | Thurs 8th Mar | 0 |  | Brian Wong | Completed
US-0021 | Planning | The group needs to deicde if we are going to make a game with truth tables. | 2 | 1 | 0 | 100% | Tues 13th Mar | 0 |  | Brian Wong | Complete
US-0022 | Programming | Paul is trying to create a leaderboard in NetBeans. | 2 | 1 week. | 0 | 100% | Tues 13th Mar | 0 |  | Brian Wong | Complete
US-0023 | Programming | Adam Wade will design the 'About' page. | 1 | 20 | 0 | 100% | Thurs 15th Mar | 0 |  | Brian Wong | complete | We needed to explain what how our application relates to technology on this page, which was quite difficult at times.
US-0024 | Programming | Barry McGettigan will set the theme of the 'Logic Gates' page to the 'Truth Table' page. | 1 | 5 | 0 | 100% | Thurs 15th Mar | 0 |  | Brian Wong | Complete
US-0025 | Research | Arnis will research how to put java flash game into project | 1 | 12 | d | 0% | Fri 30 Mar | 0 |  | Amis Lupiks | Demoted |  | To complex to get JavaMediaFrame to work in NetBeans
US-0026 | Research | Barry will make research how to put a links in the project page. | 1 | 12 | d | 0% | Fri 30 Mar | 0 |  | Amis Lupiks |  | Putting links into our project proved to be too difficult.
US-0027 | Programming | Arnis compile the project | 1 | 6 | 0 | 100% | Fri 30 Mar | 0 |  | Amis Lupiks | Completed
US-0028 | Research | Barry will research how to get his circuit game he created in flash, working in netbeans | 1 | 1 week | 0 | 100% | Fri 13 Apr | 0 |  | Barry McGettigan | Completed | getting javamediaframe to work is proving to be quite difficult.
US-0029 | Programming | Brian will try and add functionality to his truth tables game. | 1 | 1 week | 0 | 100% | Fri 13 Apr | 0 |  | Barry McGettigan | Completed | We may have to use a java animation file as an example, rather then an actual game.
US-0030 | Requirements & Design | Arnis will create a background in photoshop for our Apps pages | 2 | 12 | 0 | 100% | Tue 10 Apr | 23 |  | Barry McGettigan | Completed
US-0031 | Research | barry will investigate how to incorporate arrays into the project | 1 | 1 week | 0 | 100% | Fri 13 Apr | 0 |  | Barry McGettigan | Completed | We decided the best way to incorporate an array into our project, was by listing the top player`s who have played the game. We did this on our leaderboard page.
US-0032 | Art / Sound Assets | Arnis is researching how to put a soundbite into our app. | 3 | 1 week | 0 | 100% | Fri 13 Apr | 0 |  | Barry McGettigan | Completed | Arnis got the program to say "Welcome" when the user starts the program. Make sure you have the sound on!!!!!
US-0033 | Art / Sound Assets | Paul is researching how to put videos into our project | 2 | 1 week | d | 0% | Thur 12 Apr | 0 |  | Barry McGettigan | Demoted |  | Coding for this was far to advanced for our group.
US-0034 | Requirements & Design | We all gathered around to discuss what final colour`s and designs we were going to use. | 1 | 12 | 0 | 100% | Thur 12 Apr | 0 |  | Barry McGettigan | Completed | Brian demanded pink but the rest of the group thought it would be unsuitable
US-0035 | Requirements & Design | Brian and Arnis completed the definitions on our page with the truth tables diagrams. | 1 | 12 | 0 | 100% | Thur 12 Apr | 0 |  | Barry McGettigan | Completed
US-0036 | Build release | All our groups compiled our projects together. | 1 | 12 | 0 | 100% | Thur 12 Apr | 0 |  | Barry McGettigan | Completed | File handeling proved very difficult when compiling projects.
US-0037 | [7 empty] | 0
US-0040 | [7 empty] | 0
US-0041 | [7 empty] | 0
US-0042 | [7 empty] | 0
US-0043 | [7 empty] | 0
US-0044 | [7 empty] | 0
US-0045 | [7 empty] | 0
US-0046 | [7 empty] | 0
US-0047 | [7 empty] | 0
US-0048 | [7 empty] | 0
US-0049 | [7 empty] | 0
US-0050 | [7 empty] | 0
US-0051 | [7 empty] | 0
US-0052 | [7 empty] | 0
US-0053 | [7 empty] | 0
US-0054 | [7 empty] | 0
US-0055 | [7 empty] | 0
US-0056 | [7 empty] | 0
US-0057 | [7 empty] | 0
US-0058 | [7 empty] | 0
US-0059 | [7 empty] | 0
US-0060 | [7 empty] | 0
US-0061 | [7 empty] | 0
US-0062 | [7 empty] | 0
US-0063 | [7 empty] | 0
US-0064 | [7 empty] | 0
US-0065 | [7 empty] | 0
US-0066 | [7 empty] | 0
US-0067 | [7 empty] | 0
US-0068 | [7 empty] | 0
US-0069 | [7 empty] | 0
US-0070 | [7 empty] | 0
US-0071 | [7 empty] | 0
US-0072 | [7 empty] | 0
US-0073 | [7 empty] | 0
US-0074 | [7 empty] | 0
US-0075 | [7 empty] | 0
US-0076 | [7 empty] | 0
US-0077 | [7 empty] | 0
US-0078 | [7 empty] | 0
US-0079 | [7 empty] | 0
US-0080 | [7 empty] | 0
US-0081 | [7 empty] | 0
US-0082 | [7 empty] | 0
US-0083 | [7 empty] | 0
US-0084 | [7 empty] | 0
US-0085 | [7 empty] | 0
US-0086 | [7 empty] | 0
US-0087 | [7 empty] | 0
US-0088 | [7 empty] | 0
US-0089 | [7 empty] | 0
US-0090 | [7 empty] | 0
US-0091 | [7 empty] | 0
US-0092 | [7 empty] | 0
US-0093 | [7 empty] | 0
US-0094 | [7 empty] | 0
US-0095 | [7 empty] | 0
US-0096 | [7 empty] | 0
US-0097 | [7 empty] | 0
US-0098 | [7 empty] | 0
US-0099 | [7 empty] | 0
US-0100 | [7 empty] | 0
US-0101 | [7 empty] | 0
US-0102 | [7 empty] | 0
US-0103 | [7 empty] | 0
US-0104 | [7 empty] | 0
US-0105 | [7 empty] | 0
US-0106 | [7 empty] | 0
US-0107 | [7 empty] | 0
US-0108 | [7 empty] | 0
US-0109 | [7 empty] | 0
US-0110 | [7 empty] | 0
US-0111 | [7 empty] | 0
US-0112 | [7 empty] | 0
US-0113 | [7 empty] | 0
US-0114 | [7 empty] | 0
The value will only change if you have completed or semi-completed some task
Back
Note on L6: Author:

## Burndown
Burn Down |  |  |  | Average daily hours: | 0 | resources: | 4 | Estimated Completion date
| Date | BurnCalc | General Activity | Deliverables | Team Hours | Recorder | ScrumMaster
Sprint 0
Req's Gathering | 2012-02-02 | 1
Concept | 2012-02-07 | 120
Design | 2012-02-09 | 102
UI Mock-up | 2012-02-14 | 85
Planning | 2012-02-16 | 113
Sprint 1 | 2012-02-21 | 123
Build 1 | 2012-02-23 | 85
| 2012-02-28 | 95
| 2012-03-01 | 73
Sprint 2 | 2012-03-06 | 99
Build 2 | 2012-03-08 | 76
| 2012-03-13 | 60
| 2012-03-15 | 40
Sprint 3 | 2012-03-20 | 0
Build 3 | 2012-03-22
| 2012-03-27 | 77.75
2012-03-29
Sprint 4 | 2012-04-03 | 53.3
Test & Debug | 2012-04-05 | 47
| 2012-04-10 | 23
| 2012-04-12 |  | Submission
Each day enter burn value here
this calculation is only correct if there are no filters on in the TaskList as it depends on the currently reported total hours of work
Back

## Control
| Project Control |  | Version: | 1 | Current Sprint: | 0 | Date: | 2012-04-12 14:48
Values used in cell dropdowns |  |  |  |  | Deliverables
| Source Type | Expected |  |  | D001
|  | Unexpected |  |  | D002
|  | New Feature |  |  | D003
D004
| Cost/Complexity | 3 hours / Simple |  |  | D005
|  | 10 hours / Medium |  |  | D006
|  | 25 hours / Complex |  |  | D007
D008
| Priority | 0 |  |  | D009
|  | 1 |  |  | D010
2
3
| User Story Type | Programming
Art / Sound Assets
Research
Build release
Testing
Requirements & Design
Bug Fixing
Planning
| Status | 1 | Incomplete
|  | -1 | In Progress
|  | 0 | Completed
|  | d | Demoted
| Resources | Adam Wade
Brian Wong
Barry McGettigan
Amis Lupiks
Paul Cuffe
| Sprint | Sprint 0 - concept & plan
Sprint 1 - build 1
Sprint 2 - build 2
Sprint 3 - build 3
Sprint 4 - test and fix
Put your names here, replacing the templated text
Good to make a list of exactly what has to be delivered. So that it is in one place as a reminder of the projects objective
Back

## Example
| Burn Down |  |  |  |  | Sprint | 4
| Date | CostDue | Activity | Deliverables | SprintMaster
Sprint 0 | 2008-04-14 | 450 |  |  | Paul
| 2008-04-15 | 77 |  |  | Paul
| 2008-04-16 | 77 |  |  | Paul
| 2008-04-17 | 160 |  |  | Paul
| 2008-04-18 | 266 | Planning Meeting | Design Spec ( 4 pages ) | Paul
| 2008-04-19 | 266 |  |  | Paul
| 2008-04-20 | 266 |  |  | Paul
Sprint 1 | 2008-04-21 | 266 |  |  | Adam
| 2008-04-22 | 203 |  |  | Adam
| 2008-04-23 | 203 |  |  | Adam
| 2008-04-24 | 203 |  |  | Adam
| 2008-04-25 | 203 |  |  | Adam
| 2008-04-26 | 203 |  |  | Adam
| 2008-04-27 | 203 |  |  | Adam
Sprint 2 | 2008-04-28 | 406 | Planning Meeting | Build Demo | Mary
| 2008-04-29 | 413 |  |  | Mary
| 2008-04-30 | 378 |  |  | Mary
| 2008-05-01 | 371 |  |  | Mary
| 2008-05-02 | 229.25 |  |  | Mary
| 2008-05-03 | 220.1 |  |  | Mary
| 2008-05-04 | 215.95 |  |  | Mary
| 2008-05-05 | 171.5 |  |  | Mary
Sprint 3 | 2008-05-06 | 145.6 | Planning Meeting | Build Demo | James
| 2008-05-07 | 128.87 |  |  | James
| 2008-05-08 | 112.78 |  |  | James
| 2008-05-09 | 117.03 | Planning Meeting - Finish line |  | James
| 2008-05-10 | 103.48 |  |  | James
| 2008-05-11 | 90.78 |  |  | James
| 2008-05-12 | 73.07 | Planning Meeting | Final Build | James
| 2008-05-13 |  | Project Delivery (5pm) | XBOX360 Software, Documents | James
| 2008-05-14 |  | Project Presentation (10am) | Presentation Slides | James
Back